## Activity list
US
[12 empty] | Date format: dd-mm-yyyy (31-08-2013 for July 31st 2013) | [5 empty] | Color | Legends | Task
[19 empty] | Mandatory field | Bug
only if applicable
S.No | Month | Names |  |  | Activity |  | Est. hrs | Actual hrs |  |  | Rev Est. | Planned Dates |  |  | Actual Dates |  |  |  | Reason for late delivery / Any other specific reason
|  | Employee | Team | Supervisor | Type | Number |  | Investi- gation | Dev | Merge/ Test |  | Start Date | End Date | Need By | Start Date | End Date | Ready to Merge | Completed
1 | 2017-08-01 | Ramesh Dhandapani | PAAS | Merlin C Yesudian | US | 4986 | 13 | 4 | 7 | 2 |  | 2017-08-01 | 2017-08-11 | 2017-08-11 | 2017-08-01 | 2017-08-11 | 2017-08-11 | 2017-08-11 | Completed
2 | 2017-08-01 | Ramesh Dhandapani | PAAS | Merlin C Yesudian | US | 7671 | 42 | 6 | 30 | 6 |  | 2017-08-02 | 2017-08-16 | 2017-08-14 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | Completed
3 | 2017-08-01 | Ramesh Dhandapani | PAAS | Merlin C Yesudian | Task | 7989 | 19 | 7 | 9 | 3 |  | 2017-08-02 | 2017-08-14 | 2017-08-11 | 2017-08-03 | 2017-08-11 | 2017-08-11 | 2017-08-11 | Completed
4 | 2017-08-01 | Ramesh Dhandapani | PAAS | Merlin C Yesudian | Task | 5914 | 10 | 3 | 5 | 2 |  | 2017-08-03 | 2017-08-14 | 2017-08-14 | 2017-08-03 | 2017-08-14 | 2017-08-14 | 2017-08-14 | Completed
5 | 2017-08-01 | Ramesh Dhandapani | PAAS | Merlin C Yesudian | Task | 8226 | 24 | 6 | 16 | 2 |  | 2017-08-16 | 2017-08-24 | 2017-08-24 | 2017-08-16 | 2017-08-24 | 2017-08-24 | 2017-08-24 | Completed
6 | 2017-08-01 | Ramesh Dhandapani | PAAS | Merlin C Yesudian | US | 7744 | 34 | 8 | 20 | 6 |  | 2017-08-18 | 2017-08-31 | 2017-08-31 | 2017-08-18 | 2017-08-31 | 2017-08-31 | 2017-08-31 | Completed
7 | 2017-08-01 | Ramesh Dhandapani | PAAS | Merlin C Yesudian | US | 5441 | 20 | 6 | 10 | 4 |  | 2017-08-21 | 2017-08-31 | 2017-08-31 | 2017-08-21 | 2017-08-31 | 2017-08-31 | 2017-08-31 | Completed
Note on G7: 1. User Story (US) 2. Task 3. Bug

## Other_Metrics
S No | Name | Team Name | Supervisor Name | Month | Safety(RIF) - (Number of Recordbale safety incidents happened to HCL employees, if something happened to you mention as 1 or 0 ) | Number of defects external to ITDD - ( Number of defects external to ITDD and internal to CAT) | Quality improvement YOY - (Internal defect count applicable to HCL developers and testers as applicable get it from CAT leads) | Number of ideas accepted by Caterpillar - (Number of Accepted ideas by CAT team/Project lead, please send acceptance proof like mail) | R&E efficiency - (CAT approved $ Value for implemented idea along with approval Mail proof - example 5K$ )
1 | Ramesh Dhandapani | PAAS | Merlin C Yesudian | 2017-08-01 | 0 | 0 | 0 | 0 | 0

## Spills
S No | Name | Team Name | Supervisor Name | Month | Number of Spills external to CAT | Spill details - description of Spill | RCCA details
1 | Ramesh Dhandapani | PAAS | Merlin C Yesudian | 2017-08-01 | 0 | 0 | 0